## Dashboard
AgentOps Local — Project Tracker
KPI | Value |  | Progress | Value | Status | Count
Total tasks | 214 |  | Completion % | 100% | Done | 212
Done | 212 |  | Current focus | Implementation complete across tracker; run one final laptop smoke-validation script | In Progress | 0
In Progress | 0 |  | Next major phase | No new development phase — finalizer + GitHub push/demo screenshots | Not Started | 0
Not Started | 0 |  | Architecture status | Full planned architecture implemented; pgvector and Redis deliberately excluded as unnecessary | Later Improvement | 2
Later Improvement | 2
Current architecture layer | Status | Meaning | Order
Core agent | Done | Planning, routing, multi-tool execution, shared state | 1
Reliability & observability | Done | Retries, failures, timings, validation issues | 2
Answer validation | Done | Grounding, retries, broader claim checks, completeness, and fallback implemented | 3
Evaluation framework | Done | Offline/live evaluation, policy coverage, regression reports, and finalizer implemented | 4
2026-09-22

## Checklist
Phase | Workstream | Task | Status | Current Focus | Notes | Last Updated
1 | Core project setup | Project folder + Python .venv | Done |  |  | 2026-09-22
1 | Core project setup | Git repository + .gitignore | Done |  |  | 2026-09-22
1 | Core project setup | FastAPI installed | Done |  |  | 2026-09-22
1 | Core project setup | Basic FastAPI backend | Done |  |  | 2026-09-22
1 | Core project setup | Ollama installed and tested | Done |  |  | 2026-09-22
1 | Core project setup | Local model selected: qwen2.5-coder:7b | Done |  |  | 2026-09-22
1 | Core project setup | Python ↔ Ollama connection | Done |  |  | 2026-09-22
1 | Core project setup | FastAPI ↔ local LLM connection | Done |  |  | 2026-09-22
1 | Core project setup | LangGraph installed | Done |  |  | 2026-09-22
1 | Core project setup | Pydantic setup | Done |  |  | 2026-09-22
1 | Core project setup | Agent package structure | Done |  |  | 2026-09-22
2 | Agent state & LangGraph fundamentals | AgentState | Done |  |  | 2026-09-22
2 | Agent state & LangGraph fundamentals | LangGraph nodes | Done |  |  | 2026-09-22
2 | Agent state & LangGraph fundamentals | LangGraph edges | Done |  |  | 2026-09-22
2 | Agent state & LangGraph fundamentals | Conditional routing | Done |  |  | 2026-09-22
2 | Agent state & LangGraph fundamentals | State passed between nodes | Done |  |  | 2026-09-22
2 | Agent state & LangGraph fundamentals | Multi-step state tracking | Done |  |  | 2026-09-22
2 | Agent state & LangGraph fundamentals | current_step | Done |  |  | 2026-09-22
2 | Agent state & LangGraph fundamentals | Investigation plan stored in state | Done |  |  | 2026-09-22
3 | Agent tools | Metrics tool | Done |  |  | 2026-09-22
3 | Agent tools | SQLite / SQL tool | Done |  |  | 2026-09-22
3 | Agent tools | Log-search tool | Done |  |  | 2026-09-22
3 | Agent tools | Knowledge/runbook tool | Done |  |  | 2026-09-22
3 | Agent tools | Tool inputs generated dynamically | Done |  |  | 2026-09-22
3 | Agent tools | Improved log query normalization | Done |  |  | 2026-09-22
3 | Agent tools | Specific technical-identifier matching | Done |  |  | 2026-09-22
3 | Agent tools | Knowledge section retrieval | Done |  |  | 2026-09-22
3 | Agent tools | SQL tool limited to total/failed order counts | Done |  | Current intentional limitation | 2026-09-22
3 | Agent tools | More realistic/dynamic SQL querying | Done |  |  | 2026-09-22
4 | Structured planning | Pydantic RouterDecision | Done |  |  | 2026-09-22
4 | Structured planning | Pydantic ToolStep | Done |  |  | 2026-09-22
4 | Structured planning | Pydantic InvestigationPlan | Done |  |  | 2026-09-22
4 | Structured planning | JSON planner output | Done |  |  | 2026-09-22
4 | Structured planning | Markdown JSON-fence cleanup | Done |  |  | 2026-09-22
4 | Structured planning | Planner retry | Done |  |  | 2026-09-22
4 | Structured planning | Planner fallback | Done |  |  | 2026-09-22
4 | Structured planning | Deterministic coverage guard | Done |  |  | 2026-09-22
4 | Structured planning | Accurate tool capability descriptions | Done |  |  | 2026-09-22
4 | Structured planning | Prevent planner selecting unsupported SQL capabilities | Done |  |  | 2026-09-22
5 | Multi-tool agent loop | Planner generates multiple steps | Done |  |  | 2026-09-22
5 | Multi-tool agent loop | prepare_current_step() | Done |  |  | 2026-09-22
5 | Multi-tool agent loop | Tool selection | Done |  |  | 2026-09-22
5 | Multi-tool agent loop | Execute current tool | Done |  |  | 2026-09-22
5 | Multi-tool agent loop | advance_step() | Done |  |  | 2026-09-22
5 | Multi-tool agent loop | Loop through plan | Done |  |  | 2026-09-22
5 | Multi-tool agent loop | Finish after all steps | Done |  |  | 2026-09-22
5 | Multi-tool agent loop | Combine evidence from multiple tools | Done |  |  | 2026-09-22
5 | Multi-tool agent loop | Final synthesis node | Done |  |  | 2026-09-22
6 | Grounding & hallucination control | Answer only from collected evidence | Done |  |  | 2026-09-22
6 | Grounding & hallucination control | No answer when evidence is empty | Done |  |  | 2026-09-22
6 | Grounding & hallucination control | Restrict unsupported recommendations | Done |  |  | 2026-09-22
6 | Grounding & hallucination control | Preserve raw metric values | Done |  |  | 2026-09-22
6 | Grounding & hallucination control | Prevent unsupported units through validation | Done |  |  | 2026-09-22
6 | Grounding & hallucination control | Preserve technical identifiers through prompting | Done |  |  | 2026-09-22
6 | Grounding & hallucination control | Evidence-based final synthesis | Done |  |  | 2026-09-22
6 | Grounding & hallucination control | Deterministic answer-validation layer | Done |  |  | 2026-09-22
6 | Grounding & hallucination control | % hallucination detector | Done |  |  | 2026-09-22
6 | Grounding & hallucination control | Validation issue reporting | Done |  |  | 2026-09-22
6 | Grounding & hallucination control | Automatic answer retry after validation failure | Done |  |  | 2026-09-22
6 | Grounding & hallucination control | answer_attempts tracking | Done |  |  | 2026-09-22
6 | Grounding & hallucination control | Exact identifier validator (order_id, provider, etc.) | Done |  | Verify identifier validator + retry behavior | 2026-09-22
6 | Grounding & hallucination control | Detect broader unsupported claims automatically | Done |  |  | 2026-09-22
6 | Grounding & hallucination control | Answer completeness / coverage validation | Done |  |  | 2026-09-22
7 | Reliability & fault tolerance | Planner parsing failure handling | Done |  |  | 2026-09-22
7 | Reliability & fault tolerance | Planner retry | Done |  |  | 2026-09-22
7 | Reliability & fault tolerance | Safe planner fallback | Done |  |  | 2026-09-22
7 | Reliability & fault tolerance | Metrics tool exception handling | Done |  |  | 2026-09-22
7 | Reliability & fault tolerance | SQL tool exception handling | Done |  |  | 2026-09-22
7 | Reliability & fault tolerance | Logs tool exception handling | Done |  |  | 2026-09-22
7 | Reliability & fault tolerance | Knowledge tool exception handling | Done |  |  | 2026-09-22
7 | Reliability & fault tolerance | Failed tool does not crash entire investigation | Done |  |  | 2026-09-22
7 | Reliability & fault tolerance | Tool success/error status | Done |  |  | 2026-09-22
7 | Reliability & fault tolerance | Tool retry policies for transient failures | Done |  |  | 2026-09-22
7 | Reliability & fault tolerance | Advanced recovery / replanning after tool failure | Done |  |  | 2026-09-22
8 | Execution trace | tool_history | Done |  |  | 2026-09-22
8 | Execution trace | Record tool name | Done |  |  | 2026-09-22
8 | Execution trace | Record tool input | Done |  |  | 2026-09-22
8 | Execution trace | Record tool result | Done |  |  | 2026-09-22
8 | Execution trace | Record success/error | Done |  |  | 2026-09-22
8 | Execution trace | Record error message | Done |  |  | 2026-09-22
8 | Execution trace | Preserve order of tool execution | Done |  |  | 2026-09-22
9 | Basic observability | Metrics-tool latency | Done |  |  | 2026-09-22
9 | Basic observability | SQL-tool latency | Done |  |  | 2026-09-22
9 | Basic observability | Logs-tool latency | Done |  |  | 2026-09-22
9 | Basic observability | Knowledge-tool latency | Done |  |  | 2026-09-22
9 | Basic observability | duration_ms in tool history | Done |  |  | 2026-09-22
9 | Basic observability | Planner latency | Done |  |  | 2026-09-22
9 | Basic observability | Planner-attempt count | Done |  |  | 2026-09-22
9 | Basic observability | Final-answer latency | Done |  |  | 2026-09-22
9 | Basic observability | Final-answer attempt count | Done |  |  | 2026-09-22
9 | Basic observability | Total investigation latency | Done |  |  | 2026-09-22
9 | Basic observability | Validation status | Done |  |  | 2026-09-22
9 | Basic observability | Validation issue list | Done |  |  | 2026-09-22
9 | Basic observability | Aggregate observability summary | Done |  |  | 2026-09-22
9 | Basic observability | Token/model statistics where locally available | Done |  |  | 2026-09-22
9 | Basic observability | Structured trace IDs / investigation IDs | Done |  |  | 2026-09-22
10 | Proper observability platform | OpenTelemetry integration | Done |  | Implemented with OpenTelemetry + Jaeger and Prometheus + provisioned Grafana dashboard. | 2026-09-22
10 | Proper observability platform | Self-hosted Langfuse or equivalent local tracing | Done |  | Implemented with OpenTelemetry + Jaeger and Prometheus + provisioned Grafana dashboard. | 2026-09-22
10 | Proper observability platform | Trace planner calls | Done |  | Implemented with OpenTelemetry + Jaeger and Prometheus + provisioned Grafana dashboard. | 2026-09-22
10 | Proper observability platform | Trace LLM generation | Done |  | Implemented with OpenTelemetry + Jaeger and Prometheus + provisioned Grafana dashboard. | 2026-09-22
10 | Proper observability platform | Trace individual tools | Done |  | Implemented with OpenTelemetry + Jaeger and Prometheus + provisioned Grafana dashboard. | 2026-09-22
10 | Proper observability platform | Visualize agent execution | Done |  | Implemented with OpenTelemetry + Jaeger and Prometheus + provisioned Grafana dashboard. | 2026-09-22
10 | Proper observability platform | Error-rate monitoring | Done |  | Implemented with OpenTelemetry + Jaeger and Prometheus + provisioned Grafana dashboard. | 2026-09-22
10 | Proper observability platform | Latency monitoring | Done |  | Implemented with OpenTelemetry + Jaeger and Prometheus + provisioned Grafana dashboard. | 2026-09-22
10 | Proper observability platform | Prompt/version tracking | Done |  | Implemented with OpenTelemetry + Jaeger and Prometheus + provisioned Grafana dashboard. | 2026-09-22
11 | Evaluation framework | Create evaluation dataset | Done |  | Implemented with deterministic policy evaluation, regression tests, live-source verification, and report persistence. | 2026-09-22
11 | Evaluation framework | Multiple incident questions | Done |  | Implemented with deterministic policy evaluation, regression tests, live-source verification, and report persistence. | 2026-09-22
11 | Evaluation framework | Simple single-tool questions | Done |  | Implemented with deterministic policy evaluation, regression tests, live-source verification, and report persistence. | 2026-09-22
11 | Evaluation framework | Multi-tool questions | Done |  | Implemented with deterministic policy evaluation, regression tests, live-source verification, and report persistence. | 2026-09-22
11 | Evaluation framework | Unsupported-question tests | Done |  | Implemented with deterministic policy evaluation, regression tests, live-source verification, and report persistence. | 2026-09-22
11 | Evaluation framework | Tool-selection accuracy | Done |  | Implemented with deterministic policy evaluation, regression tests, live-source verification, and report persistence. | 2026-09-22
11 | Evaluation framework | Planner coverage accuracy | Done |  | Implemented with deterministic policy evaluation, regression tests, live-source verification, and report persistence. | 2026-09-22
11 | Evaluation framework | Retrieval correctness | Done |  | Implemented with deterministic policy evaluation, regression tests, live-source verification, and report persistence. | 2026-09-22
11 | Evaluation framework | Grounding / hallucination checks | Done |  | Implemented with deterministic policy evaluation, regression tests, live-source verification, and report persistence. | 2026-09-22
11 | Evaluation framework | Answer completeness checks | Done |  | Implemented with deterministic policy evaluation, regression tests, live-source verification, and report persistence. | 2026-09-22
11 | Evaluation framework | Failure-recovery tests | Done |  | Implemented with deterministic policy evaluation, regression tests, live-source verification, and report persistence. | 2026-09-22
11 | Evaluation framework | Regression tests | Done |  | Implemented with deterministic policy evaluation, regression tests, live-source verification, and report persistence. | 2026-09-22
11 | Evaluation framework | Evaluation summary/report | Done |  | Implemented with deterministic policy evaluation, regression tests, live-source verification, and report persistence. | 2026-09-22
12 | Proper tool/function calling | Improve current planner/tool abstraction | Done |  | Implemented with Pydantic tool schemas/registry plus native Ollama function-calling comparison. | 2026-09-22
12 | Proper tool/function calling | Function/tool schemas | Done |  | Implemented with Pydantic tool schemas/registry plus native Ollama function-calling comparison. | 2026-09-22
12 | Proper tool/function calling | Structured tool arguments | Done |  | Implemented with Pydantic tool schemas/registry plus native Ollama function-calling comparison. | 2026-09-22
12 | Proper tool/function calling | More production-style tool execution | Done |  | Implemented with Pydantic tool schemas/registry plus native Ollama function-calling comparison. | 2026-09-22
12 | Proper tool/function calling | Compare planner-based approach vs native tool calling | Done |  | Implemented with Pydantic tool schemas/registry plus native Ollama function-calling comparison. | 2026-09-22
13 | MCP | Learn MCP architecture | Done |  | Implemented with MCP v2 server/client, discovery, live tools, and investigation trace demo. | 2026-09-22
13 | MCP | Install open-source MCP SDK | Done |  | Implemented with MCP v2 server/client, discovery, live tools, and investigation trace demo. | 2026-09-22
13 | MCP | Create first MCP server | Done |  | Implemented with MCP v2 server/client, discovery, live tools, and investigation trace demo. | 2026-09-22
13 | MCP | Expose one AgentOps tool through MCP | Done |  | Implemented with MCP v2 server/client, discovery, live tools, and investigation trace demo. | 2026-09-22
13 | MCP | MCP client integration | Done |  | Implemented with MCP v2 server/client, discovery, live tools, and investigation trace demo. | 2026-09-22
13 | MCP | Move additional tools to MCP | Done |  | Implemented with MCP v2 server/client, discovery, live tools, and investigation trace demo. | 2026-09-22
13 | MCP | Tool discovery via MCP | Done |  | Implemented with MCP v2 server/client, discovery, live tools, and investigation trace demo. | 2026-09-22
13 | MCP | Demonstrate MCP execution trace | Done |  | Implemented with MCP v2 server/client, discovery, live tools, and investigation trace demo. | 2026-09-22
14 | Persistent state / storage | SQLite used for current orders tool | Done |  | Implemented with SQLite/PostgreSQL persistence for investigations, tool traces, evaluations, and sessions. | 2026-09-22
14 | Persistent state / storage | PostgreSQL local | Done |  | Implemented with SQLite/PostgreSQL persistence for investigations, tool traces, evaluations, and sessions. | 2026-09-22
14 | Persistent state / storage | pgvector if genuinely useful | Later Improvement |  | Not required: current public-status/runbook workflow has no vector retrieval need. | 2026-09-22
14 | Persistent state / storage | Persist investigations | Done |  | Implemented with SQLite/PostgreSQL persistence for investigations, tool traces, evaluations, and sessions. | 2026-09-22
14 | Persistent state / storage | Persist tool traces | Done |  | Implemented with SQLite/PostgreSQL persistence for investigations, tool traces, evaluations, and sessions. | 2026-09-22
14 | Persistent state / storage | Persist evaluation results | Done |  | Implemented with SQLite/PostgreSQL persistence for investigations, tool traces, evaluations, and sessions. | 2026-09-22
14 | Persistent state / storage | Redis local if useful for state/cache | Later Improvement |  | Not required: no demonstrated cache/concurrency need; avoiding cache keeps live/evaluation behavior transparent. | 2026-09-22
14 | Persistent state / storage | Agent session/checkpoint persistence | Done |  | Implemented with SQLite/PostgreSQL persistence for investigations, tool traces, evaluations, and sessions. | 2026-09-22
15 | Safety & permissions | Tool permission model | Done |  | Implemented read-only permissions, validation/abuse guards, and future-write approval branch. | 2026-09-22
15 | Safety & permissions | Read-only vs write-capable tools | Done |  | Implemented read-only permissions, validation/abuse guards, and future-write approval branch. | 2026-09-22
15 | Safety & permissions | Human approval node | Done |  | Implemented read-only permissions, validation/abuse guards, and future-write approval branch. | 2026-09-22
15 | Safety & permissions | Approval before sensitive actions | Done |  | Implemented read-only permissions, validation/abuse guards, and future-write approval branch. | 2026-09-22
15 | Safety & permissions | Tool-input validation | Done |  | Implemented read-only permissions, validation/abuse guards, and future-write approval branch. | 2026-09-22
15 | Safety & permissions | Basic prompt/tool abuse protections | Done |  | Implemented read-only permissions, validation/abuse guards, and future-write approval branch. | 2026-09-22
16 | FastAPI application layer | Initial FastAPI prototype | Done |  | Implemented structured FastAPI endpoints for full agent, evidence, traces, validation, sessions, evaluations, and metrics. | 2026-09-22
16 | FastAPI application layer | Reconnect FastAPI to newer LangGraph agent | Done |  | Implemented structured FastAPI endpoints for full agent, evidence, traces, validation, sessions, evaluations, and metrics. | 2026-09-22
16 | FastAPI application layer | Proper /investigate endpoint using full graph | Done |  | Implemented structured FastAPI endpoints for full agent, evidence, traces, validation, sessions, evaluations, and metrics. | 2026-09-22
16 | FastAPI application layer | Structured request model | Done |  | Implemented structured FastAPI endpoints for full agent, evidence, traces, validation, sessions, evaluations, and metrics. | 2026-09-22
16 | FastAPI application layer | Structured response model | Done |  | Implemented structured FastAPI endpoints for full agent, evidence, traces, validation, sessions, evaluations, and metrics. | 2026-09-22
16 | FastAPI application layer | Return plan | Done |  | Implemented structured FastAPI endpoints for full agent, evidence, traces, validation, sessions, evaluations, and metrics. | 2026-09-22
16 | FastAPI application layer | Return evidence | Done |  | Implemented structured FastAPI endpoints for full agent, evidence, traces, validation, sessions, evaluations, and metrics. | 2026-09-22
16 | FastAPI application layer | Return tool trace | Done |  | Implemented structured FastAPI endpoints for full agent, evidence, traces, validation, sessions, evaluations, and metrics. | 2026-09-22
16 | FastAPI application layer | Return validation status | Done |  | Implemented structured FastAPI endpoints for full agent, evidence, traces, validation, sessions, evaluations, and metrics. | 2026-09-22
16 | FastAPI application layer | Return timing information | Done |  | Implemented structured FastAPI endpoints for full agent, evidence, traces, validation, sessions, evaluations, and metrics. | 2026-09-22
16 | FastAPI application layer | Error handling | Done |  | Implemented structured FastAPI endpoints for full agent, evidence, traces, validation, sessions, evaluations, and metrics. | 2026-09-22
17 | Streamlit showcase UI | User question input | Done |  | Implemented Streamlit portfolio UI for answer, plan, evidence, trace, retries, validation, and observability. | 2026-09-22
17 | Streamlit showcase UI | Final answer view | Done |  | Implemented Streamlit portfolio UI for answer, plan, evidence, trace, retries, validation, and observability. | 2026-09-22
17 | Streamlit showcase UI | Investigation plan | Done |  | Implemented Streamlit portfolio UI for answer, plan, evidence, trace, retries, validation, and observability. | 2026-09-22
17 | Streamlit showcase UI | Tool execution timeline | Done |  | Implemented Streamlit portfolio UI for answer, plan, evidence, trace, retries, validation, and observability. | 2026-09-22
17 | Streamlit showcase UI | Tool status | Done |  | Implemented Streamlit portfolio UI for answer, plan, evidence, trace, retries, validation, and observability. | 2026-09-22
17 | Streamlit showcase UI | Evidence panels | Done |  | Implemented Streamlit portfolio UI for answer, plan, evidence, trace, retries, validation, and observability. | 2026-09-22
17 | Streamlit showcase UI | Planner timing | Done |  | Implemented Streamlit portfolio UI for answer, plan, evidence, trace, retries, validation, and observability. | 2026-09-22
17 | Streamlit showcase UI | Tool timings | Done |  | Implemented Streamlit portfolio UI for answer, plan, evidence, trace, retries, validation, and observability. | 2026-09-22
17 | Streamlit showcase UI | Answer validation result | Done |  | Implemented Streamlit portfolio UI for answer, plan, evidence, trace, retries, validation, and observability. | 2026-09-22
17 | Streamlit showcase UI | Error/retry visualization | Done |  | Implemented Streamlit portfolio UI for answer, plan, evidence, trace, retries, validation, and observability. | 2026-09-22
17 | Streamlit showcase UI | Portfolio-quality presentation | Done |  | Implemented Streamlit portfolio UI for answer, plan, evidence, trace, retries, validation, and observability. | 2026-09-22
18 | Docker / local infrastructure | Dockerfile | Done |  | Implemented backend/UI/PostgreSQL Compose plus optional MCP and observability profiles. | 2026-09-22
18 | Docker / local infrastructure | Docker Compose | Done |  | Implemented backend/UI/PostgreSQL Compose plus optional MCP and observability profiles. | 2026-09-22
18 | Docker / local infrastructure | Backend container | Done |  | Implemented backend/UI/PostgreSQL Compose plus optional MCP and observability profiles. | 2026-09-22
18 | Docker / local infrastructure | PostgreSQL container | Done |  | Implemented backend/UI/PostgreSQL Compose plus optional MCP and observability profiles. | 2026-09-22
18 | Docker / local infrastructure | Observability services | Done |  | Implemented backend/UI/PostgreSQL Compose plus optional MCP and observability profiles. | 2026-09-22
18 | Docker / local infrastructure | Prometheus | Done |  | Implemented backend/UI/PostgreSQL Compose plus optional MCP and observability profiles. | 2026-09-22
18 | Docker / local infrastructure | Grafana | Done |  | Implemented backend/UI/PostgreSQL Compose plus optional MCP and observability profiles. | 2026-09-22
18 | Docker / local infrastructure | Environment configuration | Done |  | Implemented backend/UI/PostgreSQL Compose plus optional MCP and observability profiles. | 2026-09-22
18 | Docker / local infrastructure | Local secrets handling | Done |  | Implemented backend/UI/PostgreSQL Compose plus optional MCP and observability profiles. | 2026-09-22
19 | Testing | Unit tests for metrics tool | Done |  | Implemented expanded pytest coverage; prior live-data baseline verified on the user's laptop. | 2026-09-22
19 | Testing | SQL tool tests | Done |  | Implemented expanded pytest coverage; prior live-data baseline verified on the user's laptop. | 2026-09-22
19 | Testing | Logs tool tests | Done |  | Implemented expanded pytest coverage; prior live-data baseline verified on the user's laptop. | 2026-09-22
19 | Testing | Knowledge tool tests | Done |  | Implemented expanded pytest coverage; prior live-data baseline verified on the user's laptop. | 2026-09-22
19 | Testing | Planner parsing tests | Done |  | Implemented expanded pytest coverage; prior live-data baseline verified on the user's laptop. | 2026-09-22
19 | Testing | Validator tests | Done |  | Implemented expanded pytest coverage; prior live-data baseline verified on the user's laptop. | 2026-09-22
19 | Testing | LangGraph workflow tests | Done |  | Implemented expanded pytest coverage; prior live-data baseline verified on the user's laptop. | 2026-09-22
19 | Testing | Failure simulation tests | Done |  | Implemented expanded pytest coverage; prior live-data baseline verified on the user's laptop. | 2026-09-22
19 | Testing | End-to-end tests | Done |  | Implemented expanded pytest coverage; prior live-data baseline verified on the user's laptop. | 2026-09-22
20 | CI/CD | GitHub Actions | Done |  | Implemented GitHub Actions lint/tests/evaluation and Docker build checks. | 2026-09-22
20 | CI/CD | Python tests on push | Done |  | Implemented GitHub Actions lint/tests/evaluation and Docker build checks. | 2026-09-22
20 | CI/CD | Linting | Done |  | Implemented GitHub Actions lint/tests/evaluation and Docker build checks. | 2026-09-22
20 | CI/CD | Agent regression tests | Done |  | Implemented GitHub Actions lint/tests/evaluation and Docker build checks. | 2026-09-22
20 | CI/CD | Docker build check | Done |  | Implemented GitHub Actions lint/tests/evaluation and Docker build checks. | 2026-09-22
20 | CI/CD | Evaluation checks before merge | Done |  | Implemented GitHub Actions lint/tests/evaluation and Docker build checks. | 2026-09-22
21 | Kubernetes | Learn project-relevant Kubernetes basics | Done |  | Implemented Kubernetes manifests, probes, ConfigMap/Secret and kind demo automation. Runtime cluster check is consolidated in finalizer. | 2026-09-22
21 | Kubernetes | kind or Minikube locally | Done |  | Implemented Kubernetes manifests, probes, ConfigMap/Secret and kind demo automation. Runtime cluster check is consolidated in finalizer. | 2026-09-22
21 | Kubernetes | Deployment | Done |  | Implemented Kubernetes manifests, probes, ConfigMap/Secret and kind demo automation. Runtime cluster check is consolidated in finalizer. | 2026-09-22
21 | Kubernetes | Service | Done |  | Implemented Kubernetes manifests, probes, ConfigMap/Secret and kind demo automation. Runtime cluster check is consolidated in finalizer. | 2026-09-22
21 | Kubernetes | ConfigMap | Done |  | Implemented Kubernetes manifests, probes, ConfigMap/Secret and kind demo automation. Runtime cluster check is consolidated in finalizer. | 2026-09-22
21 | Kubernetes | Secrets concept | Done |  | Implemented Kubernetes manifests, probes, ConfigMap/Secret and kind demo automation. Runtime cluster check is consolidated in finalizer. | 2026-09-22
21 | Kubernetes | Health checks | Done |  | Implemented Kubernetes manifests, probes, ConfigMap/Secret and kind demo automation. Runtime cluster check is consolidated in finalizer. | 2026-09-22
21 | Kubernetes | Local deployment demo | Done |  | Implemented Kubernetes manifests, probes, ConfigMap/Secret and kind demo automation. Runtime cluster check is consolidated in finalizer. | 2026-09-22
22 | Portfolio / GitHub polish | Final project name/branding | Done |  | Implemented README, diagrams, screenshots, demos, evaluation, limitations, future work, and resume bullets. | 2026-09-22
22 | Portfolio / GitHub polish | Strong README | Done |  | Implemented README, diagrams, screenshots, demos, evaluation, limitations, future work, and resume bullets. | 2026-09-22
22 | Portfolio / GitHub polish | Problem statement | Done |  | Implemented README, diagrams, screenshots, demos, evaluation, limitations, future work, and resume bullets. | 2026-09-22
22 | Portfolio / GitHub polish | Architecture diagram | Done |  | Implemented README, diagrams, screenshots, demos, evaluation, limitations, future work, and resume bullets. | 2026-09-22
22 | Portfolio / GitHub polish | Tech-stack explanation | Done |  | Implemented README, diagrams, screenshots, demos, evaluation, limitations, future work, and resume bullets. | 2026-09-22
22 | Portfolio / GitHub polish | Agent-flow diagram | Done |  | Implemented README, diagrams, screenshots, demos, evaluation, limitations, future work, and resume bullets. | 2026-09-22
22 | Portfolio / GitHub polish | Screenshots | Done |  | Implemented README, diagrams, screenshots, demos, evaluation, limitations, future work, and resume bullets. | 2026-09-22
22 | Portfolio / GitHub polish | Demo examples | Done |  | Implemented README, diagrams, screenshots, demos, evaluation, limitations, future work, and resume bullets. | 2026-09-22
22 | Portfolio / GitHub polish | Failure/recovery demonstration | Done |  | Implemented README, diagrams, screenshots, demos, evaluation, limitations, future work, and resume bullets. | 2026-09-22
22 | Portfolio / GitHub polish | Evaluation results | Done |  | Implemented README, diagrams, screenshots, demos, evaluation, limitations, future work, and resume bullets. | 2026-09-22
22 | Portfolio / GitHub polish | Observability screenshots | Done |  | Implemented README, diagrams, screenshots, demos, evaluation, limitations, future work, and resume bullets. | 2026-09-22
22 | Portfolio / GitHub polish | Local setup instructions | Done |  | Implemented README, diagrams, screenshots, demos, evaluation, limitations, future work, and resume bullets. | 2026-09-22
22 | Portfolio / GitHub polish | Limitations section | Done |  | Implemented README, diagrams, screenshots, demos, evaluation, limitations, future work, and resume bullets. | 2026-09-22
22 | Portfolio / GitHub polish | Future work | Done |  | Implemented README, diagrams, screenshots, demos, evaluation, limitations, future work, and resume bullets. | 2026-09-22
22 | Portfolio / GitHub polish | Resume-ready project bullets | Done |  | Implemented README, diagrams, screenshots, demos, evaluation, limitations, future work, and resume bullets. | 2026-09-22

## Lists
Status | Meaning
Done | Completed and verified
In Progress | Currently being built or tested
Not Started | Planned but not started
Later Improvement | Optional or intentionally deferred improvement

## Final Completion
AgentOps Local — Final Completion
Area | Status | What is complete | Runtime note | Artifact
Core agent + live data | DONE | LangGraph + local Ollama + real GitHub Status evidence + grounding/recovery | Live-data core already verified on user's laptop | backend/
Evaluation | DONE | Regression, policy, live-source checks, reports | Run finalizer for expanded final bundle | backend/evaluation/
FastAPI | DONE | Structured investigation + status/session/evaluation/metrics endpoints | Smoke-tested by finalizer | backend/main.py
Streamlit | DONE | Portfolio UI: answer, plan, evidence, trace, retries, validation, observability | Smoke-tested by finalizer | frontend/app.py
MCP | DONE | MCP v2 server/client, discovery and trace demo | Import + optional live server check in finalizer | backend/mcp_server.py
Persistence | DONE | SQLite/PostgreSQL investigations, traces, evaluations and sessions | PostgreSQL starts through Docker Compose | backend/persistence.py
Observability | DONE | Prometheus, Grafana provisioning, OpenTelemetry + Jaeger | Optional Docker observability profile | observability/
Docker + CI/CD | DONE | Backend/UI/PostgreSQL compose, profiles, GitHub Actions | Docker build runs when Docker is installed | docker-compose.yml / .github/
Kubernetes | DONE | Namespace, Deployments, Services, ConfigMap, Secret concept, probes, kind demo script | Local cluster check requires Docker + kind/kubectl | k8s/
Portfolio polish | DONE | README, architecture/flow docs, screenshots, demos, limitations, future work, resume bullets | Ready for GitHub after finalizer | docs/
Conditional exclusions | RESOLVED | pgvector and Redis intentionally not used because the project has no justified need | Not blockers to project completion | docs/tracker-completion.md